## Sheet1
| Task | Responsible | Status | Due Date | Year 1
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Lead: Make an explicit commitment to reduce suicide deaths | Communicate H3S Commitment to Zero Suicide Initiative
| ◦ Department-wide email from H3S Director |  | Completed
| ◦ Introduce Zero Suicide/provide training to H3S division directors |  | In Process
| ◦ Develop and disseminate overarching H3S P&P |  | To Be Completed
| ◦ Ongoing communication via department emails/newsletters |  | Ongoing
Convene Zero Suicide Implementation Team
| ◦ Recruit representatives from each division |  | Completed
| ◦ Include input from individuals with lived experience |  | In Process
| ◦ Review training options for all H3S employees (e.g., CALM) |  | In Process
| ◦ Discuss current and/or future policies and procedures - Ensure they include review of adverse outcomes - Ensure they include support for staff |  | To Be Completed
| ◦ Design evaluation plan to assess impact |  | To Be Completed
| ◦ Establish data collection plan |  | To Be Completed
| ◦ Review and update work plan |  | Ongoing
Zero Suicide Organizational Self Study
| ◦ Completion of self-study for H3S department |  | In Process
Zero Suicide Workforce Survey for H3S staff
| ◦ Aggregate results of survey for all H3S divisions |  | In Process
| ◦ Review and utilize results to inform next steps |  | In Process
Reduce Stigma and Create a Culture of Recovery in H3S
| ◦ Complete environmental scan to assess current state |  | To Be Completed
| ◦ Examine existing models and best practices for creating a culture of recovery in the workplace |  | To Be Completed
| ◦ Make recommendations to Director of H3S & executive team |  | To Be Completed
Train: Develop a competent, confident, caring workforce | Completion of MH First Aid by all H3S staff
| ◦ Communicate training requirement to all staff |  | Completed
| ◦ Advise staff of training opportunities |  | Ongoing
| ◦ Monitor and communicate training completion rates |  | In Process
| ◦ Develop H3S department P&P related to training requirement |  | To Be Completed
Train Staff/Ongoing Communication of Zero Suicide Philosophy
Ongoing
Training on lethal means restriction (CALM)
Assess Skills and Confidence for Providing Suicide Safer Care
| ◦ Zero Suicide Workforce Survey for H3S staff |  | In Process
| ◦ Deploy clinical and non-clinical versions of the survey |  | In Process
Training Should be Repeated & Skills Reassessed Periodically
Identify: Systematically identify and assess suicide risk (Screening/Assessing & Formulating Risk) | Provide Support & Guidance Across Divisions as Needed Related to Identifying Individuals at Risk for Suicide
◦ Identify divisions/programs that will utilize formal screening processes
◦ How do we support and serve persons within the Department that are not on a clinical pathway?
Assist Non-Clinical Divisions/Programs with Establishing Pathway to Care
◦ Assist with establishing protocol for referral to care
◦ Assist with establishing a mechanism to alert appropriate staff about suicide risk
◦ Facilitate/support debrief activites post-identification/referral
Assist Clinical Divisions/Programs with Selecting & Implementing Screening Measures
◦ Provide support and guidance as needed
◦ Establish ongoing communication with H3S
Coordinate with existing Health Centers division implementation team
Coordinate with existing Behavioral Health division implementation team
Assist Clinical Divisions/Programs with Selecting & Implementing Risk Assessment and Formulation
◦ Provide support and guidance as needed
◦ Establish ongoing communication with H3S
Coordinate with existing Health Centers division implementation team
Coordinate with existing Behavioral Health division implementation team
Engage: Ensure every person has a suicide care management plan, or pathway to care, that is both timely and adequate to meet his or her needs | Provide Support & Guidance Related to Designing Suicide Care Management Policies (Clinical Divisions/Programs)
◦ Assist with establishing criteria for suicide care management plans as needed
Provide Support and Guidance Related to Implementing Suicide Care Management Practices (Clinical Divisions/Programs)
◦ Hold ongoing meetings to discuss implementation strategies and results
◦ Establish a set of "best practices" for implementing safer suicide care
◦ Assess communication of suicide risk between divisions for clients receiving multiple services
Treat: Use effective, evidence-based treatments that directly target suicidality | Communicate/Support Need to Provide Evidence-Based Interventions that are Suicide-Specific
◦ Assess and evaluate fidelity to core treatment elements
◦ Assess and evaluate client outcomes
Communicate/Support Need to Provide Care in the Least Restrictive Setting
◦ Encourage/establish collaboration with other agencies and partners to provide options in terms of treatment settings and modalities - Crisis Center Hotline and Follow-Up - Brief Intervention and Follow-Up - Outpatient Care - Emergency Respite Care (peers) - Partial Hospitalization - Inpatient Hospitalization
Transition: Provide continuous contact & support, especially after acute care | Assist/Support Development of Policies for Safe Care Transitions
◦ Clients referred within H3S divisions/programs and across divisions/programs
◦ Clients transferred to another provider/organization or county department in the community
◦
◦
Prioritize Assistance to Clients as They Make Transitions in Their Care
◦ May include contacting other providers, sending records, contacting client after making transition to new provider
◦ Warm hand-offs, rapid referrals, caring contacts, & client education
Emphasize Need for Documentation Protocol for Care Transitions
◦
Improve: Apply a data-driven improvement approach to inform system changes | Establish Baseline of Previous Suicide Deaths and Attempts in the County
| ◦ Connect with Clackamas County Medical Examiner's Office to determine what data is available. |  | In Process
Identify Zero Suicide Data Elements to Collect to Assess Fidelity
◦ Utilize Data Elements document as a guide
Monitor Periodically to Determine that Data are Being Captured
◦ Set schedule to review a selection of charts
Analyze Data at Regular Intervals to Determine Fidelity
◦ Analyze data at 6 months and 12 months
Assess Client Satisfaction across H3S Divisions
Assess Staff Satisfaction and Understanding of Zero Suicide Philosophy
Share and Review Results with Leadership and Staff